## MOM NOV'22 (hidden)
MINUTES OF MEETING
PN INTERNATIONAL PVT. LTD.
(PNI)
Name of the Meeting |  |  | Monthly Meeting - IT & Innovation
Venue |  |  | On Team Call and IT CABIN | [7 empty] | Meeting No. | 2
Date of Meeting |  |  | 2023-01-06 | [7 empty] | Date for Next Meeting | 07th Feb'22
Chairman |  |  | VINAY KUMAR GUPTA | [7 empty] | Co-Ordinator | Abhishek Mohan
Members Present |  |  | Abhishek Mohan, Gaurav Gupta, Keshav Kashyap,Neelesh Kumar, Pawan Kumar, Shiv Kumar, Shivam Sharma, Sumit Jaiswal, Vinay Kumar Gupta | [7 empty] | Members Absent | Sanjay Singh
Sr.No | Department Name | Process Segment | UNIT Location | Issues / Suggestions Raised by Executive (Name) | Issues / Suggestions Raised | Issue-SPOC | Department of SPOC | HOD of SPOC | Suggestions / Action Taken | Month | Date of Issue Raised (DD-MM-YYYY) | Proposed Closure Date by SPOC | Actual Closure Date | Proposed TAT (as per SPOC) | Final TAT | Difference (TAT) | Status (OPEN / HOLD / CLOSED) | Remark
1 | IT & Innovation | ITi | EOU | Sumit Jaiswal | Open tickets of Exit Employee Discuss with Sampark Solutions | Abhishek Mohan | IT i | Vinay Kumar Gupta |  | DECEMBER | 2023-01-06 | 2/7/2023 15-Mar-23 |  |  |  |  | OPEN
2 | IT & Innovation | ITi | EOU | Sumit Jaiswal | MRM Points to be raised in ITSM ticket Portal which needs to be discussed with IT i | All Dept. | IT i | Vinay Kumar Gupta |  | DECEMBER | 2023-01-06 | 2023-02-07 |  |  |  |  | OPEN
3 | IT & Innovation | ITi | EOU | Shiv Kumar | Auto Cad system to be converted to official LAN Unit-3 | Sanjay Singh | IT i | Vinay Kumar Gupta |  | DECEMBER | 2023-01-06 | 2023-01-15 | 2023-02-16 |  |  |  | CLOSED
4 | IT & Innovation | ITi | EOU | Shiv Kumar | Printer Replace in Press Shop | Abhishek Mohan | IT i | Vinay Kumar Gupta |  | DECEMBER | 2023-01-06 | 2023-01-15 | 2023-01-15 |  |  |  | CLOSED
5 | IT & Innovation | ITi | EOU | Gaurav Gupta | Nice Label software needs to be install in Sandila Unit | Abhishek Mohan | IT i | Vinay Kumar Gupta |  | DECEMBER | 2023-01-06 | 2023-01-20 | 2023-01-11 |  |  |  | CLOSED
6 | IT & Innovation | ITi | EOU | Sumit Jaiswal | Unlicensed SQL Devloper Software needs to be removed in all Departments. | Abhishek Mohan | IT i | Vinay Kumar Gupta |  | DECEMBER | 2023-01-06 | 2023-02-07 | 2023-01-15 |  |  |  | CLOSED
7 | IT & Innovation | ITi | EOU | Pawan Verma | Smart Track Network Device must be relocate | Neelesh Mishra | IT i | Vinay Kumar Gupta |  | DECEMBER | 2023-01-06 | 2/7/2023 15-Mar-23 |  |  |  |  | OPEN
Sr.No | Department Name | Process Segment | UNIT Location | Issues / Suggestions Raised by Executive (Name) | Issues / Suggestions Raised | Issue-SPOC | Department of SPOC | HOD of SPOC | Suggestions / Action Taken | Month | Date of Issue Raised (DD-MM-YYYY) | Proposed Closure Date by SPOC | Actual Closure Date | Proposed TAT (as per SPOC) | Final TAT | Difference (TAT) | Status (OPEN / HOLD / CLOSED) | Remark
1 | IT & Innovation | ITi | EOU | Vinay Kumar Gupta | Meeting with saurabh mailk and aman regarding monthly system update. Any changes done in iso, memo, circular etc would be informed to it on regular basis. | Abhishek mohan | IT & Innovation | Vinay Kumar Gupta | Point has been discussed with Director IT and this report is not required in MRM | 2022-11-01 | 2022-12-07 | 2022-12-15 | 2023-01-06 |  |  |  | Closed
2 | IT & Innovation | ITi | EOU | Vinay Kumar Gupta | java web services on erp server for both vesions simultaneously. To be checked with DBA for production. | Sumit Jaiswal | IT & Innovation | Vinay Kumar Gupta |  | 2022-11-01 | 2022-12-07 | 2022-12-15 | 2023-01-06 |  |  |  | Closed
3 | IT & Innovation | ITi | EOU | Vinay Kumar Gupta | Java web services to be tested on clone . Latest java version to be installed and tested with clone and produciton along with latest and old firefox browser. | Sumit Jaiswal/Sanjay Singh/ Pawan Kumar | IT & Innovation | Vinay Kumar Gupta |  | 2022-11-01 | 2022-12-07 | 2022-12-15 | 2023-01-06 |  |  |  | Closed
4 | IT & Innovation | ITi | EOU | Vinay Kumar Gupta | Changes in ITSM including infra, Erp, Software.Additional slides need to be added in monthly presentation for each vertical | All IT Vertical | IT & Innovation | Vinay Kumar Gupta |  | 2022-11-01 | 2022-12-07 | 2022-01-07 | 2023-01-06 |  |  |  | Closed
5 | IT & Innovation | ITi | EOU | Vinay Kumar Gupta | BSC to be updated / reviwed every month. | Abhishek mohan/Sumit Jaiswal/Keshav Kashyap | IT & Innovation | Vinay Kumar Gupta | WIP | 2022-11-01 | 2022-12-07 | 2022-01-07 |  |  |  |  | OPEN | BSC will be presented from Mar23 onwards
6 | IT & Innovation | ITi | EOU | Shiv Kumar | One Tab to be sent to UNIT3 for machine shifting | Abhishek Mohan/Shivam Sharma | IT & Innovation | Vinay Kumar Gupta |  | 2022-11-01 | 2022-12-07 | 2022-12-15 | 2023-01-06 |  |  |  | Closed
7 | IT & Innovation | ITi | EOU | Neelesh Mishra | Raj Barcode Slave server to be hosted in unit 2 | Abhishek Mohan/ Keshav Kashyap/Raj Barcode | IT & Innovation | Vinay Kumar Gupta |  | 2022-11-01 | 2022-12-07 | 2022-01-07 | 2023-01-06 |  |  |  | Closed
8 | IT & Innovation | ITi | EOU | Neelesh Mishra | IT Infra implementation at Juno Casting/Unit-2 extention | Abhishek Mohan | IT & Innovation | Vinay Kumar Gupta | Email to be sent for plant layout to Jawed Sir for IT infra implimentation in Unit 2 extended plant | 2022-11-01 | 2022-12-07 | 2022-12-15 |  |  |  |  | OPEN | CCTV camera to installed on ext. plant. After that all IT infra devices will be installed on floor to avoid any theft and damage to equipment.
9 | IT & Innovation | ITi | EOU | Abhishek Mohan | Intractive display board installed at Unit-2 Photon Hall for safety of the same CCTV Camera is required. | Neelesh Mishra | IT & Innovation | Vinay Kumar Gupta | CCTV camera installation in Photon hall unit 2 | 2022-11-01 | 2022-12-07 | 2022-12-15 | 2023-01-05 |  |  |  | Closed
10 | IT & Innovation | ITi | EOU | Gaurav Gupta | Backup ILL Link is required at Sandila Plant for uninterrupted | Abhishek Mohan | IT & Innovation | Vinay Kumar Gupta | 50 Mbps connection at sandila Unit | 2022-11-01 | 2022-12-07 | 2022-01-07 | 2023-01-23 |  |  |  | Closed
11 | IT & Innovation | ITi | EOU | Gaurav Gupta | KSS ID for Sandila IT Department need to be created. | Keshav Kashyap | IT & Innovation | Vinay Kumar Gupta |  | 2022-11-01 | 2022-12-07 | 2022-12-07 |  |  |  |  | Closed
12 | IT & Innovation | ITi | EOU | Gaurav Gupta | Discussion regarding OT with Mayank Srivastava for Sandila Unit | Vinay Kumar Gupta | IT & Innovation | Vinay Kumar Gupta |  | 2022-11-01 | 2022-12-07 | 2022-01-07 | 2023-01-06 |  |  |  | Closed
13 | IT & Innovation | ITi | EOU | Keshav Kashyap | Backup of IIS of 0.3 and 1.106 servers to be done on regular scheduled basis. | Abhishek Mohan/Keshav Kashyap | IT & Innovation | Vinay Kumar Gupta |  | 2022-11-01 | 2022-12-07 | 1/7/2022 15-Mar-23 |  |  |  |  | OPEN
14 | IT & Innovation | ITi | EOU | Keshav Kashyap | One ManPower Required for Buisness Analyst in IT Department | Vinay Kumar Gupta | IT & Innovation | Vinay Kumar Gupta |  | 2022-11-01 | 2022-12-07 | 2022-01-07 | 2023-01-06 |  |  |  | Closed
15 | IT & Innovation | ITi | EOU | Neelesh Mishra | Unit 2 Network report analysis required | Abhishek Mohan | IT & Innovation | Vinay Kumar Gupta |  | 2022-11-01 | 2022-12-07 | 2022-01-07 | 2023-01-06 |  |  |  | Closed
16 | IT & Innovation | ITi | EOU | Neelesh Mishra | Firewall Access of unit 2 | Abhishek Mohan | IT & Innovation | Vinay Kumar Gupta |  | 2022-11-01 | 2022-12-07 | 2022-12-15 | 2022-12-09 |  |  |  | Closed
17 | IT & Innovation | ITi | EOU | Vinay Kumar Gupta | Asset Management Sheet need to be circulated in All Units | Abhishek Mohan | IT & Innovation | Vinay Kumar Gupta |  | 2022-11-01 | 2022-12-07 | 1/7/2022 15-Apr-23 |  |  |  |  | OPEN
18 | IT & Innovation | ITi | EOU | Vinay Kumar Gupta | Tab report format to be shared | Gaurav Gupta | IT & Innovation | Vinay Kumar Gupta | Report should be kept at centeralised for regular update on teams | 2022-11-01 | 2022-12-07 | 2022-12-07 |  |  |  |  | Closed
19 | IT & Innovation | ITi | EOU | Neelesh Mishra | Ticket need to be rasised for IT issues in Unit 2 properly. | Vinay Kumar Gupta | IT & Innovation | Vinay Kumar Gupta | ITSM resolver id to be created for Raj Bar Code. | 2022-11-01 | 2022-12-07 | 2022-12-15 |  |  |  |  | OPEN | Issue resolved. Under observation
20 | IT & Innovation | ITi | EOU | Vinay Kumar Gupta | Enablement of change event , incident, options under ITSM portal . To be checked with the vendor | Abhishek Mohan | IT & Innovation | Vinay Kumar Gupta |  | 2022-11-01 | 2022-12-07 | 2022-01-07 | 2023-01-20 | 2023-01-20 |  |  | Closed
21 | IT & Innovation | ITi | EOU | Vinay Kumar Gupta | ERP Prod need to be tested on MPLS | Abhishek Mohan | IT & Innovation | Vinay Kumar Gupta |  | 2022-11-01 | 2022-12-07 | 12/15/2022 15-Mar-23 |  | 2023-02-07 |  |  | OPEN
22 | IT & Innovation | ITi | EOU | Vinay Kumar Gupta | PNI ticket category wise - closure of tickets against total tickets slide to be added in same side | Abhishek Mohan | IT & Innovation | Vinay Kumar Gupta |  | 2022-11-01 | 2022-12-07 | 2022-12-15 | 2023-01-06 |  |  |  | Closed
23 | IT & Innovation | ITi | EOU | Sumit Jaiswal | Email id updation in oracle HRMS | HR DEPT. | IT & Innovation | Vinay Kumar Gupta |  | 2022-11-01 | 2022-12-07 | 2022-12-15 |  |  |  |  | OPEN
24 | IT & Innovation | ITi | EOU | Sanjay Singh | Notification required in case of Dept Change (ex. Anuj singh and Manoj Kumar Verma Unit 3) | HR DEPT. | IT & Innovation | Vinay Kumar Gupta | Consolidated monthly report required from HR | 2022-11-01 | 2022-12-07 | 2022-12-15 |  | 2023-02-07 |  |  | OPEN
Note on F23: Admin:

## TO-DO
MINUTES OF MEETING
PN INTERNATIONAL PVT. LTD.
(PNI)
Name of the Meeting |  | Stand-up Meeting - DevOps
Date of Meeting |  | 2023-07-11
Members Present |  | Dimpal Gupta, Shashank Gautam,Jitendra Tiwari,Keshav Kashyap | Member Absent | Ajay Pratap Singh
Sr. No | Executive (Name) | Task Description | Task Priority | Start Date | Remarks
1 | Jitendra Kumar | The department needs to be merged into the DMS portal | Medium | 2023-06-30 | WIP, to be done on 10 July, Review and Testing Pending
2 |  | VMS Upgrade 2 (Need to add Super Admin Login) to be upload on staging | Medium | 2023-07-06 | Done
3 |  | TPD Portal (Approval process and make dashboard dynamic) | High |  | Hold
1 | Dimpal Gupta | Safety Work Permit project | High | 2023-06-19 | WIP
2 |  | VMS Upgrade 2 finalise | High | 2023-07-03 | Done
3 |  | SSL Production check on staging | High | 2023-07-03 | WIP
4 |  | Finalise open project | High | 2023-07-04 | WIP
5 |  | VMS Upgrade 2 and OHC Enhancement to be upload on staging | High | 2023-07-06 | Done
1 | Shashank Gautam | NCR Portal Revamp | Medium | 2023-06-30 | WIP
2 |  | OHC Enhancement New | Medium | 2023-07-07 | WIP
|  | PPR and Development Sheet Enhancement | High | 2023-07-11 | New Task
1 | Ajay Pratap Singh | SOW of Calibration | High |  | WIP, To be done by tommorow, Hold
2 |  | eNX 2.0 user manual | High |  | New Task, In Queue
3 |  | OHC Enhancement Review | Medium | 2023-07-03 | WIP
4 |  | Schedule Training for Gate In - Gate Out | Medium | 2023-07-04 | New Task
5 |  | Device deployment on CNC Section IOT | Medium | 2023-07-04 | WIP
6 |  | PPR and development sheet follow up | Medium | 2023-07-03 | WIP, to be done by today
7 |  | BRD of TPD | High | 2023-07-10 | New Task
8 |  | IOT Device Configuration | High | 2023-07-10 | New Task
1 | Keshav Kashyap | Rectify calibration issue of users | High |  | WIP, Reminder 2
2 |  | SSL deployment on PROD | High | 2023-06-28 | WIP, Reminder 2, It's urgent
3 |  | Upload 3-4 solution from production to staging for SSL | Medium | 2023-06-28 | WIP
4 |  | Master Supplier Management | High | 2023-07-03 | WIP
5 |  | SRS for OHC Medicine | Medium |  | Review Pending at Keshav Sir, Reminder 3, Review Done need some changes in SRS, To be done on 23 June 2023. Delay by Shashank,Done,Pending for Review
6 |  | SOW of eNX Portal | Medium |  | Done, Under Review at Keshav Sir end, Reminder 1 to Keshav sir
7 |  | SOW of OHC Medicine | High |  | Pending for review, Reminder 3
8 |  | SRS for eNX | High |  | Pending for review, Reminder 3
9 |  | BRD of Calibration | High |  | Pending for review, Reminder 3
10 |  | Review Calibration Portal issue | High |  | New Task, Pending at Keshav Sir end, To be done today, Reminder 1 to Keshav sir
11 |  | BRD of Safety Work Permit | High |  | New Task , Pending for review
12 |  | SOW of Safety Work Permit | High |  | WIP, To be completed by today, Pending for Review
13 |  | Resolve - Server was not working | High |  | Done

## Completed
MINUTES OF MEETING
PN INTERNATIONAL PVT. LTD.
(PNI)
Name of the Meeting |  | Stand-up Meeting - DevOps
Last Date of Meeting |  | 2023-07-11
Members Present |  | Ajay Pratap Singh, Dimpal Gupta, Jitendra Kumar, Shashank Gautam,Keshav Kashyap | Member Absent
Sr. No | Executive (Name) | Task Description | Task Priority | Start Date | End Date | Remarks
1 | Jitendra Kumar | ENX KI testing | Medium |  | 2023-06-28 | This point forward to Keshav Sir, Reminder 4, Done
2 |  | DMS Drawing Zoom in Zoom out functionality to be added | Medium |  | 2023-06-28 | Reminder 1 to Jitendra, Keshav sir will not be available 3-4 days due to this reason it will be upload on Monday. Done, Need to test on Prod, this point forward to Keshav Sir, Reminder 4 to Keshav sir, Done
3 |  | VMS Upgrade 2 (Need to add Super Admin Login) | Medium | 2023-06-23 | 2023-07-06 | WIP, started on Thursday, Review Pending, Done
4 |  | VMS Upgrade 2 (Need to add Super Admin Login) to be upload on staging | Medium | 2023-07-06 | 2023-07-11 | Done
1 | Dimpal Gupta | PPR and development sheet validation need to be done. | High |  | 2023-06-26 | Development Complete, Under review from user, Enhnacement taken and working on it, under Review, Done
2 |  | OHC Enhancement to be upload on staging server. | High |  | 2023-06-28 | Done
3 |  | VMS Upgrade 2 finalise | High | 2023-07-03 | 2023-07-11 | Done
4 |  | VMS Upgrade 2 and OHC Enhancement to be upload on staging | High | 2023-07-06 | 2023-07-11 | Done
1 | Shashank Gautam | PPR Review to user | High |  | 2023-06-26 | Label review done and PPR is pending, Done
2 |  | PPR and development sheet Enhancement | High |  | 2023-06-27 | To be completed on Monday, under Review, Done
3 |  | Level 2 OHC Portal Enhancement | High |  | 2023-06-28 | WIP, To be completed by today's afternoon, Done
4 |  | PPR and development sheet Enhancement | High |  | 2023-06-28 | To be completed on Monday, under Review, Done
5 |  | New Report in OHC | High | 2023-07-05 | 2023-07-06 | Done
6 |  | Technicals of SRS for OHC Medicine | Medium |  | 2023-06-28 | WIP, To be completed by today's evenning, Reminder 1, Done
7 |  | Label Printing query to be corrected for correct data | High | 2023-06-30 | 2023-07-06 | Done
8 |  | OHC Enhancement Review | Medium | 2023-07-03 | 2023-07-06 | Done
1 | Ajay Pratap Singh | BRD of Vender Registration Portal | High |  | 2023-06-26 | Done
2 |  | New IOT's to be register on asset register | High |  | 2023-06-28 | To be completed by today, Done
3 |  | IoT Device Configuration | High |  | 2023-07-05 | Done
1 | Ajay Pratap Singh | SRS for OHC Medicine | Medium |  |  | Review Pending at Keshav Sir, Reminder 3, Review Done need some changes in SRS, To be done on 23 June 2023. Delay by Shashank,Done,Pending for Review, Done
2 |  | SOW of eNX Portal | Medium |  |  | Done, Under Review at Keshav Sir end, Reminder 1 to Keshav sir, Done
3 |  | SOW of OHC Medicine | High |  |  | Done
4 |  | SRS for eNX | High |  |  | Done
5 |  | BRD of Calibration | High |  |  | Done
6 |  | Review Calibration Portal issue | High |  |  | New Task, Pending at Keshav Sir end, To be done today, Reminder 1 to Keshav sir,Done
8 |  | BRD of Safety Work Permit | High |  |  | Done
9 |  | SOW of Safety Work Permit | High |  |  | Done
1 | Keshav Kashyap | Presentation over DevOps project presentation | High |  | 2023-06-26 | Done
2 |  | Need to be connect a call for KI eNX | High |  | 2023-06-26 | WIP, Reminder 1, Done
3 |  | DMS Drawings convert from PDF to HTML | High |  | 2023-06-28 | Done
4 |  | 5 Tickets to be completed | Medium |  | 2023-06-28 | Done
5 |  | DMS Drawings convert from PDF to HTML | High | 2023-06-28 | 2023-06-28 | Done
6 |  | VMS V2 Review | Medium | 2023-06-28 | 2023-06-28 | Done
7 |  | DMS session with Jitendra for Department merge | Medium | 2023-06-28 | 2023-06-28 | Done
8 |  | DMS follow up | Medium | 2023-07-04 | 2023-07-05 | Done

## MOM JAN'23 (hidden)
MINUTES OF MEETING
PN INTERNATIONAL PVT. LTD.
(PNI)
Name of the Meeting |  |  | Monthly Meeting - IT & Innovation
Venue |  |  | On Team Call and IT CABIN | [7 empty] | Meeting No. | 3
Date of Meeting |  |  | 2023-02-25 | [7 empty] | Date for Next Meeting | 07th Mar'23
Chairman |  |  | VINAY KUMAR GUPTA | [7 empty] | Co-Ordinator | Abhishek Mohan
Members Present |  |  | Abhishek Mohan, Gaurav Gupta,Neelesh Kumar, Pawan Kumar, Shiv Kumar, Shivam Sharma, Sumit Jaiswal, Vinay Kumar Gupta | [7 empty] | Members Absent | Keshav Kasyap
Sr.No | Department Name | Process Segment | UNIT Location | Issues / Suggestions Raised by Executive (Name) | Issues / Suggestions Raised | Issue-SPOC | Department of SPOC | HOD of SPOC | Suggestions / Action Taken | Month | Date of Issue Raised (DD-MM-YYYY) | Proposed Closure Date by SPOC | Actual Closure Date | Proposed TAT (as per SPOC) | Final TAT | Difference (TAT) | Status (OPEN / HOLD / CLOSED) | Remark
1 | IT & Innovation | ITi | EOU | Sumit Jaiswal | Open tickets of Exit Employee Discuss with Sampark Solutions | Abhishek Mohan | IT i | Vinay Kumar Gupta |  | DECEMBER | 2023-01-06 | 07-02-2023 25-03-2023 |  |  |  |  | OPEN
2 | IT & Innovation | ITi | EOU | Sumit Jaiswal | MRM Points to be raised in ITSM ticket Portal which needs to be discussed with IT i | Vinay Kumar Gupta | IT i | Vinay Kumar Gupta |  | DECEMBER | 2023-01-06 | 2023-02-07 |  |  |  |  | OPEN
3 | IT & Innovation | ITi | EOU | Shiv Kumar | Auto Cad system to be converted to official LAN Unit-3 | Sanjay Singh | IT i | Vinay Kumar Gupta |  | DECEMBER | 2023-01-06 | 2023-01-15 | 2023-02-16 |  |  |  | Closed
4 | IT & Innovation | ITi | EOU | Shiv Kumar | Printer Replace in Press Shop | Abhishek Mohan | IT i | Vinay Kumar Gupta |  | DECEMBER | 2023-01-06 | 2023-01-15 | 2023-01-15 |  |  |  | Closed
5 | IT & Innovation | ITi | EOU | Gaurav Gupta | Nice Label software needs to be install in Sandila Unit | Abhishek Mohan | IT i | Vinay Kumar Gupta |  | DECEMBER | 2023-01-06 | 2023-01-20 | 2023-01-15 |  |  |  | Closed
6 | IT & Innovation | ITi | EOU | Sumit Jaiswal | Unlicensed SQL Devloper Software needs to be removed in all Departments. | Abhishek Mohan | IT i | Vinay Kumar Gupta |  | DECEMBER | 2023-01-06 | 2023-02-07 | 2023-01-15 |  |  |  | Closed
7 | IT & Innovation | ITi | EOU | Pawan Verma | Smart Track Network Device must be relocate | Neelesh Mishra | IT i | Vinay Kumar Gupta |  | DECEMBER | 2023-01-06 | 07-02-2023 15-03-23 |  |  |  |  | OPEN
Sr.No | Department Name | Process Segment | UNIT Location | Issues / Suggestions Raised by Executive (Name) | Issues / Suggestions Raised | Issue-SPOC | Department of SPOC | HOD of SPOC | Suggestions / Action Taken | Month | Date of Issue Raised (DD-MM-YYYY) | Proposed Closure Date by SPOC | Actual Closure Date | Proposed TAT (as per SPOC) | Final TAT | Difference (TAT) | Status (OPEN / HOLD / CLOSED) | Remark
1 | IT & Innovation | ITi | EOU | Vinay Kumar Gupta | Meeting with saurabh mailk and aman regarding monthly system update. Any changes done in iso, memo, circular etc would be informed to it on regular basis. | Abhishek mohan | IT & Innovation | Vinay Kumar Gupta | Point has been discussed with Director IT and this report is not required in MRM | 2022-11-01 | 2022-12-07 | 2022-12-15 | 2023-01-06 |  |  |  | Closed
2 | IT & Innovation | ITi | EOU | Vinay Kumar Gupta | java web services on erp server for both vesions simultaneously. To be checked with DBA for production. | Sumit Jaiswal | IT & Innovation | Vinay Kumar Gupta |  | 2022-11-01 | 2022-12-07 | 2022-12-15 | 2023-01-06 |  |  |  | Closed
3 | IT & Innovation | ITi | EOU | Vinay Kumar Gupta | Java web services to be tested on clone . Latest java version to be installed and tested with clone and produciton along with latest and old firefox browser. | Sumit Jaiswal/Sanjay Singh/ Pawan Kumar | IT & Innovation | Vinay Kumar Gupta |  | 2022-11-01 | 2022-12-07 | 2022-12-15 | 2023-01-06 |  |  |  | Closed
4 | IT & Innovation | ITi | EOU | Vinay Kumar Gupta | Changes in ITSM including infra, Erp, Software.Additional slides need to be added in monthly presentation for each vertical | All IT Vertical | IT & Innovation | Vinay Kumar Gupta |  | 2022-11-01 | 2022-12-07 | 2022-01-07 | 2023-01-06 |  |  |  | Closed
5 | IT & Innovation | ITi | EOU | Vinay Kumar Gupta | BSC to be updated / reviwed every month. | Abhishek mohan/Sumit Jaiswal/Keshav Kashyap | IT & Innovation | Vinay Kumar Gupta | WIP | 2022-11-01 | 2022-12-07 | 2022-01-07 |  |  |  |  | OPEN
6 | IT & Innovation | ITi | EOU | Shiv Kumar | One Tab to be sent to UNIT3 for machine shifting | Abhishek Mohan/Shivam Sharma | IT & Innovation | Vinay Kumar Gupta |  | 2022-11-01 | 2022-12-07 | 2022-12-15 | 2023-01-06 |  |  |  | Closed
7 | IT & Innovation | ITi | EOU | Neelesh Mishra | Raj Barcode Slave server to be hosted in unit 2 | Abhishek Mohan/ Keshav Kashyap/Raj Barcode | IT & Innovation | Vinay Kumar Gupta |  | 2022-11-01 | 2022-12-07 | 2022-01-07 | 2023-01-06 |  |  |  | Closed
8 | IT & Innovation | ITi | EOU | Neelesh Mishra | IT Infra implementation at Juno Casting/Unit-2 extention | Abhishek Mohan | IT & Innovation | Vinay Kumar Gupta | Email to be sent for plant layout to Jawed Sir for IT infra implimentation in Unit 2 extended plant | 2022-11-01 | 2022-12-07 | 2022-12-15 |  |  |  |  | OPEN
9 | IT & Innovation | ITi | EOU | Abhishek Mohan | Intractive display board installed at Unit-2 Photon Hall for safety of the same CCTV Camera is required. | Neelesh Mishra | IT & Innovation | Vinay Kumar Gupta | CCTV camera installation in Photon hall unit 2 | 2022-11-01 | 2022-12-07 | 2022-12-15 |  |  |  |  | OPEN
10 | IT & Innovation | ITi | EOU | Gaurav Gupta | Backup ILL Link is required at Sandila Plant for uninterrupted | Abhishek Mohan | IT & Innovation | Vinay Kumar Gupta | 50 Mbps connection at sandila Unit | 2022-11-01 | 2022-12-07 | 2022-01-07 |  |  |  |  | OPEN
11 | IT & Innovation | ITi | EOU | Gaurav Gupta | KSS ID for Sandila IT Department need to be created. | Keshav Kashyap | IT & Innovation | Vinay Kumar Gupta |  | 2022-11-01 | 2022-12-07 | 2022-12-07 |  |  |  |  | Closed
12 | IT & Innovation | ITi | EOU | Gaurav Gupta | Discussion regarding OT with Mayank Srivastava for Sandila Unit | Vinay Kumar Gupta | IT & Innovation | Vinay Kumar Gupta |  | 2022-11-01 | 2022-12-07 | 2022-01-07 | 2023-01-06 |  |  |  | Closed
13 | IT & Innovation | ITi | EOU | Keshav Kashyap | Backup of IIS of 0.3 and 1.106 servers to be done on regular scheduled basis. | Abhishek Mohan/Keshav Kashyap | IT & Innovation | Vinay Kumar Gupta |  | 2022-11-01 | 2022-12-07 | 2022-01-07 |  |  |  |  | OPEN
14 | IT & Innovation | ITi | EOU | Keshav Kashyap | One ManPower Required for Buisness Analyst in IT Department | Vinay Kumar Gupta | IT & Innovation | Vinay Kumar Gupta |  | 2022-11-01 | 2022-12-07 | 2022-01-07 | 2023-01-06 |  |  |  | Closed
15 | IT & Innovation | ITi | EOU | Neelesh Mishra | Unit 2 Network report analysis required | Abhishek Mohan | IT & Innovation | Vinay Kumar Gupta |  | 2022-11-01 | 2022-12-07 | 2022-01-07 | 2023-01-06 |  |  |  | Closed
16 | IT & Innovation | ITi | EOU | Neelesh Mishra | Firewall Access of unit 2 | Abhishek Mohan | IT & Innovation | Vinay Kumar Gupta |  | 2022-11-01 | 2022-12-07 | 2022-12-15 | 2022-12-09 |  |  |  | Closed
17 | IT & Innovation | ITi | EOU | Vinay Kumar Gupta | Asset Management Sheet need to be circulated in All Units | Abhishek Mohan | IT & Innovation | Vinay Kumar Gupta |  | 2022-11-01 | 2022-12-07 | 2022-01-07 |  |  |  |  | OPEN
18 | IT & Innovation | ITi | EOU | Vinay Kumar Gupta | Tab report format to be shared | Gaurav Gupta | IT & Innovation | Vinay Kumar Gupta | Report should be kept at centeralised for regular update on teams | 2022-11-01 | 2022-12-07 | 2022-12-07 |  |  |  |  | Closed
19 | IT & Innovation | ITi | EOU | Neelesh Mishra | Ticket need to be rasised for IT issues in Unit 2 properly. | Vinay Kumar Gupta | IT & Innovation | Vinay Kumar Gupta | ITSM resolver id to be created for Raj Bar Code. | 2022-11-01 | 2022-12-07 | 2022-12-15 |  |  |  |  | OPEN
20 | IT & Innovation | ITi | EOU | Vinay Kumar Gupta | Enablement of change event , incident, options under ITSM portal . To be checked with the vendor | Abhishek Mohan | IT & Innovation | Vinay Kumar Gupta |  | 2022-11-01 | 2022-12-07 | 2022-01-07 |  | 2023-01-20 |  |  | OPEN
21 | IT & Innovation | ITi | EOU | Vinay Kumar Gupta | ERP Prod need to be tested on MPLS | Abhishek Mohan | IT & Innovation | Vinay Kumar Gupta |  | 2022-11-01 | 2022-12-07 | 2022-12-15 |  | 2023-02-07 |  |  | OPEN
22 | IT & Innovation | ITi | EOU | Vinay Kumar Gupta | PNI ticket category wise - closure of tickets against total tickets slide to be added in same side | Abhishek Mohan | IT & Innovation | Vinay Kumar Gupta |  | 2022-11-01 | 2022-12-07 | 2022-12-15 | 2023-01-06 |  |  |  | Closed
23 | IT & Innovation | ITi | EOU | Sumit Jaiswal | Email id updation in oracle HRMS | HR DEPT. | IT & Innovation | Vinay Kumar Gupta |  | 2022-11-01 | 2022-12-07 | 2022-12-15 |  |  |  |  | OPEN
24 | IT & Innovation | ITi | EOU | Sanjay Singh | Notification required in case of Dept Change (ex. Anuj singh and Manoj Kumar Verma Unit 3) | HR DEPT. | IT & Innovation | Vinay Kumar Gupta | Consolidated monthly report required from HR | 2022-11-01 | 2022-12-07 | 2022-12-15 |  | 2023-02-07 |  |  | OPEN
Note on F23: Admin:

## Table002 (Page 1) (hidden)
S.No. | Division / Deptt | Issues Discussed | Responsibilities | Target Date | Action Taken / Update | Remarks
1 | IT Governance | In ITSM Portal, changes is to be made mandatory to provide/update TDOD on each ticket for Resolver. | Abishek Mohan | 30th Oct'22
2 | IT Governance | A TDOD column is to be added in Ticket Dashboard along with other columns. This column will populate TDOD mentioned in the ticket by Resolver. | Abishek Mohan | 30th Oct'22
2 | Digital & Online | Employee acivation/ deactivation option is to be developed on Email ID Creation/Deactivation portal. So that HODs can raise request for creation of IDs for several portals of New Joinees. | Pankaj Kumar Singh | 01st Dec'22
3 | ITi | FAQ for ITSM to be created and shared by all ITi Departments and to be shared with Mr. Abhishek Mohan. | Infra Team | 14th Nov'22
4 | ITi | The password reset option is to be enabled for Apex portal. | Amit Vikram Singh | 14th Nov'22
5 | ITi | Balance Score Card need to be prepared for all ITi Team. | All Team Members | 14th Nov'22
6 | ITi | Quote has been received from Oracle for OIC. This is to be explored more for clarity and meetings to be done with Oracle people for negotiations. | Amit Vikram Singh | 14th Nov'22
7 | ITi | IT Portal access to be given to KSF Dubai for logging all IT related tickets. | Saurabh Tyagi | 30th Oct'22
8 | ITi | Karam IT Policy is to be finlised by Nov'22. | Jyoti & Vinay | Nov'22 End
9 | ITi | After recieivng the SLA Netwerok report from Airtel, Infra Team has to check and report. | Saurabh Tyagi | Every Month
10 | ITi | A feasibility is to be checked for sending payment link along with Invoice to Dealers from ERP. | Amit Vikram Singh | 14th Nov'22 | Amit, need to arrange a internal meeting with finance team to check the feasibility.
11 | ITi | A clause - "Frieght is to be paid by Dealer" need to be added in invoice which is less than 1 lac | Amit Vikram Singh | 14th Nov'22
12 | ITi | Feasibility and procedure to be checked for sending Product Test Certificate is to be sent along with Invoice in ERP. | Amit Vikram Singh | 14th Nov'22