## NCR Sprint
SN. | Task | Start Date | Target Date | Completion Date | Revised Date | Status | Completed By | Remark
Sprint 1 | Create DB and setup Application | 2023-06-20 | 2023-06-20 |  |  | Open
| User Login | 2023-06-20 | 2023-06-20 |  |  | Open
Sprint 2 | Generate NCR | 2023-06-21 | 2023-06-22 |  |  | Open
| View NCR | 2023-06-22 | 2023-06-22 |  |  | Open
| Test & Review | 2023-06-22 | 2023-06-22 |  |  | Open
Sprint 3 | Report | 2023-06-23 | 2023-06-23 |  |  | Open
| Print/Export | 2023-06-23 | 2023-06-23 |  |  | Open
| TEST & Review | 2023-06-23 | 2023-06-23 |  |  | Open
Note - for reference check sheet 3

## Project BackLog
Sr. No. | Task Name | Task Description | Status | Assigned to | Start Date | End Date | Duration | % Complete | Remarks
Execution Forms
9 | User Login | Login page to be created so that user can login in application with their credntials. | Pending | Shashank | 2023-06-20 | 2023-06-23
12 | Generate NCR (Non Conformance Report) | NCR No, Date, PO, MRN No, Item Code, Vendor, Contact, Phone, Address, Email, Item Description, Detail of Non-Conformance, Total Received, Total Rejected, Add Attachment (Total attachment 4 needed) | Pending | Shashank | 2023-06-20 | 2023-06-23
Reports
15 | Report | As per the format | Pending | Shashank | 2023-06-20 | 2023-06-23
16 | View/Export | As per the format | Pending | Shashank | 2023-06-20 | 2023-06-23
18 | Print | As per the format | Pending | Shashank | 2023-06-20 | 2023-06-23
Note - for reference check sheet 3

## Sheet3
Generated_date | Ncr_No | VENDOR | Item_Code | MRN | Details | Email | Description | PO_Number | Total_Received | Total_Reject
2023-06-03 | 724(23-24) | MEGHDOOT PACKAGING (UTTARANCHAL) | PMMC161-02 | 230860003398 | During folding the carton getting teared off. | pavan@le-intl.co.in | PRINTED MASTER CARTON, (IRUDEK) (ART. WORK: REV. 03) (SIZE : 1510X320X330MM (OD) tolerance of + - 5 mm) FOR 7 FEET TRIPOD, CARTON MAY BE USED ALONG WITH EPE : PMEPE08, STYLE : FULL FLAP RSC,SPECIFICATION | 23820003932 | 42 no. | 42 no.
2023-06-03 | 725(23-24) | MATERIAL MOVELL (INDIA) PVT LTD | SA-17W(01.2) | 230860003394 | Wrong item received. | sumit@materialmovell.com | SWIVEL WHEEL WITH LOCKING 50MM X 25MM, MAKE:SUPO | 22820027035 | 75 no. | 75 no.
2023-06-15 | 726(23-24) | KARAM SAFETY PRIVATE LIMITED | ID03 | 220860021238 | tesst | vishal@karam.in | AMERICAN ID PLATE - BLACK ID03 | 22820027036 | 19 | 21