## DEVELOPMENT SHEET
Format No. : QF/RD/27
Rev. No. : 01
DATE : 02-08-19
S.No | New Product Description | Picture | Ref. No. | PPR No: | Status of current actions under plan | Customer | Resp | Target Date | Revised Date | Certification Status | Sample to be sent for trial (KRATOS & Gary) | Item creation, BOM & Routing | Translation Status | REMARK
Hooks & Connectors
1 | Aluminium Rebar Hook |  | PN136(SW) | PNI/R&D/2022-2023/844 | Body trimming & machining to be done | GARY | BKY | 2023-02-17
[5 empty] | Testing to be done |  | BKY | 2023-02-18
Pulley
2 | Unidirectional Double Pulley |  | AP019 | PNI/R&D/2016-2017/387 | Assembly to be done(5 Nos.) | KARAM | BKY | Ready |  | Started | YES | Not Started | Not Started
[5 empty] | Communication for EN567 testing to started from 3rd Party |  | AS | Done
[5 empty] | New Latch to be design & Developed |  | AS | ??
[5 empty] | Thumb Guide assembly to be done |  | AS | 2023-02-16
3 | Aluminium Ratchet Pulley |  | AP031 | PNI/R&D/2021-2022/795 | AP-031(17) Aluminium Cover T1 sample to be arranged | GARY | BKY | 2023-02-20 |  | Not Started | Yes | Not Started | Not Started
[5 empty] | Drawing to be made & Approved |  | BKY | ??
Anchor
4 | Dead Weight Anchor |  | SA33 |  | Bottom Plate moulding to be done(Hardness 45 to 50 Shor A) | KARAM | AY | 2023-02-16
[5 empty] | Threaded Locking pin (Dome type cover on the locking pin) |  | BKY | 2023-02-15
5 | Constent force Energy Absorber Post |  | SA38C/ SA38A | PNI/R&D/2021-2022/815 | Final testing to be done in 2.5 mm SS Strip plate | KARAM | BKY | 2023-02-13 |  | NA | Yes | Not started | Not Started
[5 empty] | Spring to be ordered 1000 nos.PR to be realesed 15.02.2023 |  | BKY | 2023-02-15
[5 empty] | Embosing trial to be taken in Richcam |  | AS | 2023-02-13
6 | AirCraft Hanger |  | PAH01 | PNI/R&D/2022-2023/832 | Drawing to be made & Approved | KARAM | AS | ?? |  | Not Started | No | Not started | Not Started
[5 empty] | Tested sample to be review |  | AS | 2023-02-15
7 | New Toggle Type Anchor |  | SA124 | PNI/R&D/2022-2023/834 | Drawing to be made | KRATOS | BKY | 2023-01-23
[5 empty] | Discuss awaited between Anant Sir & Cedric |  | BKY | 2023-02-14
8 | Ladder Support |  | SA125 | PNI/R&D/2022-2023/835 | Bender Die to be made | GARY | PKY | 2023-02-28
[5 empty] | Ladder support bottom target price to be amended from WIPE & shared with Gary Comment awaited from Gary |  | BKY | ??
9 | Anchor |  | SA126 | PNI/R&D/2022-2023/845 | Testing to be done |  | BKY | Done
[5 empty] | UIM & TDS to be made |  | BKY | 2023-02-17
[5 empty] | BUTYL TAPE DOUBLE SIDED OPENABLE SIZE:- 180MM X 30MM , Colour:- Black PRS to be made 100 Nos.(228237854) |  | BKY | 2023-02-21
Rectractable Blocks
10 | Sealed Block |  | SLBL20R | PNI/R&D/2017-2018/516 | IP 68 internal testing to be done | KARAM | BKY | 2023-02-15 |  | Certified | YES | Not Started | Not Started
11 | Sealed Block |  | SLBL30R | PNI/R&D/2017-2018/508 | IP 68 internal testing to be done | KARAM | BKY | 2023-02-15 |  | Certified | YES | Not Started | Not Started
[5 empty] | Universal Bracket for Retrieval, Item Code, BOM Routing Cost Sheet to be made |  | BKY | 2023-02-16
12 | Retrieval block |  | SLBL175 FT | PNI/R&D/2019-2020/699 | Drawing to be made | KRATOS | AS | 2023-02-15 |  | Not Started | YES | Not Started | Not Started
13 | Automatic Decender Block |  | PCGS-30AD | PNI/R&D/2014-2015/166 | Testing to be done with new assembly | KARAM | BKY | 2023-02-15
[5 empty] | Drawing to be made & approved |  | BKY | ??
[5 empty] | New Pinion to be ordered 25 Nos. PRS no. 228235728 |  | BKY | 2023-02-20
14 | Tool Lanyard |  | TL10(DW) | PNI/R&D/2022-2023/837 | Drawing to be made | DEWALT | BKY | ??
[5 empty] | Upper Casing & Lower Casing mould to be sourced |  | AY | 2023-02-28
15 | Rectractable Fall Arrester |  | PCWB-8.5FT(LE) | PNI/R&D/2020-2021/780 | Drawings to be finalized | KARAM | BKY | 2023-02-20 | [5 empty] | New Drawing
[5 empty] | BOM Routing & Cost Sheet to be finalized |  | BKY | 2023-02-20
[5 empty] | Product translation to be done |  | BKY | 2023-02-20
Tripods & Winch
16 | Foot Ascender |  | PN415 | PNI/R&D/2019-2020/702 | Body Bending to be done | KARAM | BKY | 2023-02-17
[5 empty] | Left Body bending to be done |  | BKY | Hold due to Testing resul of Right side Body
17 | DESCENDER(MILAN) |  | PN412 | PNI/R&D/2017-2018/530 | Testing to be done | KARAM | AS | ?? |  | Under Testing(In House) | YES | Not Started | Not Started
18 | ASCENDER (LOV TAZ) |  | PN421 | PNI/R&D/2022-2023/819 | To be discussed with Anant Sir for final Design | KRATOS | BKY | 2023-02-14
[5 empty] | Tentative Drawing to be made |  | BKY | ??
19 | Descender |  | PN419 | PNI/R&D/2022-2023/838 | New prototype sample to be prepared | KARAM | BKY | 2023-02-25
[5 empty] | Tentative Drawing to be made |  | BKY | ??
20 | Capstan Winch |  | PN818AC |  | Design to be made |  | BKY | 2023-02-17
Horizontal & Vertical life line
21 | Tripod |  | SA43(15') | PNI/R&D/2020-2021/770 | Drawing to be approved | KARAM | BKY | ?? |  | Not Started | NA | Not Started | Not Started
[5 empty] | Rail to be made |  | BKY | 2023-02-18
22 | Beam Anchor |  | SA08L(18inch) | PNI/R&D/2020-2021/755 | SA27L cost sheet to be made with SA110 Clamping Bracket | K STRONG (USA) | BKY | 2023-02-14
23 | Carriage Body |  | PN-4000(40) |  | 3D modle to be shared quotation awaited from Hi Tech | KARAM | BKY | 2023-02-17
Davit Arm
24 | Hitch Mounting Sleeve |  | DA05 |  | New sample to be prepared (12Nos.) for certification |  | BKY | 2023-02-17
[5 empty] | Testing to be done 50x50 internal testing(Sample to be prepared) |  | BKY | 2023-02-17
25 | Car Tow Fixture |  | DA05 |  | Car Tow drawing to be made |  | BKY | 2023-02-18
Rope Grabs
26 | Rope Grab |  | RG18 | PNI/R&D/2019-2020/684 | 3 nos. sanple to be prepared with all changes | KARAM | BKY | 2023-02-15 |  | Not Started | YES | Not Started | Not Started
[5 empty] | Drawing to be made & Approved |  | BKY | ??
27 | Progression Lanyard |  | PRP04 | PNI/R&D/2021-2022/781 | Testing to be done | KARAM | BKY | 2023-02-14
[5 empty] | Drawing to be amended through ECN |  | BKY | 2023-02-03
28 | Descender |  | RG20(ASAP) | PNI/R&D/2020-2021/756 | Rope Driver pin dia to be increase in 3D Modle (4mm Dia) quotation and sample awaited from vendor | KARAM | AS | 2023-02-20 |  | Not Started | YES | Not Started | Not Started
[5 empty] | RG-20(01) Body Cover drilling firxture to be made |  | PK | ??
[5 empty] | Drawing to be approved |  | BKY | ??
29 | Rope Grab |  | RG021 | PNI/R&D/2022-2023/821 | Final Assembly to be done with all changes | KRATOS | BKY | 154-02-2023
[5 empty] | Drawing to be amended |  | BKY | ??
30 | Rope Grab |  | RG023 | PNI/R&D/2022-2023/839 | Assembly to be done | KRATOS | BKY | 2023-02-14
[5 empty] | Karabiner Stopper for PN106 hand mould to be made As per Leo |  | BKY | Done
31 | Vertic Rope Grab |  | RG024 | PNI/R&D/2022-2023/840 | Drawing to be made & Approved | KRATOS | BKY | 2023-02-20
32 | Openable Rope Grab |  | RG025 | PNI/R&D/2022-2023/846 | Drawing to be made | KARAM | BKY | ??
Accessories
33 | Lower Bracket Assembly |  | PN-800(54) |  | New desingn to be made |  | BKY | 2023-02-17
34 | Walkway FLS mounting sandwich mounting plates for Extrimity |  | ?? |  | Drawing to be made & Approved |  | BKY | 2023-02-14
35 | Walkway FLS mounting sandwich mounting plates for Intermidiate |  | ?? |  | Drawing to be made & Approved |  | BKY | 2023-02-14
36 | Mounting Bracket |  | PN-800(44) |  | Drawing to be changed through ECN |  | BKY | 2023-02-14
37 | Pass Thru Intermidiate |  | PN-7500(03.3) |  | Fixture to be amended |  | PK | 2023-02-15
[5 empty] | Welding to be done |  | BKY | 2023-02-16
39 | Davit guard rail |  | DA11 | PNI/R&D/2017-2018/512 | Final prototype to be made | Gary | BKY | 2023-02-20
[5 empty] | Spring (SPSP130) to be sourced PRS No. (228234142 |  | BKY | Received
[5 empty] | MS pipe to be sourced(OD:-40mm & thickness:-2mm PRS No. 228234951 |  | BKY | Received
[5 empty] | Project sheet to be made |  | BKY | 2023-02-14
Moulding
40 | Climbing Helmet |  | PN592 | PNI/R&D/2016-2017/306 | Harness Connector front & Black Locking to be increase(Mould to be amended) | KARAM | AY | 2023-02-05 |  | Not Started | YES | Not Started | Not Started
[5 empty] | Drawing to be updated |  | AY | ??
41 | Lanyard Keeper |  | LK04 | NA | Drawing to be Approved | DEWALT | BKY | 2023-02-04 |  | Not Started | NA | Not Started | Not Started
42 | Rectractable Fall Arrester |  | KTGS-30 | PNI/R&D/2022-2023/841 | Mould to be sourced | KRATOS | AY | 2023-02-15
[5 empty] | Drawing to be approved |  | BKY | 2022-12-25
43 | Rectractable Fall Arrester |  | KTGS-30R | PNI/R&D/2022-2023/842 | Mould to be sourced | KRATOS | AY | 2023-02-15
[5 empty] | Drawing to be approved |  | BKY | 2022-12-27
44 | Rectractable Fall Arrester |  | TPGS-10 | PNI/R&D/2022-2023/843 | Protection Cage Mould to be made | K-STRONG | AY | 2023-02-15
[5 empty] | Drawing to be approved |  | BKY | ??
45 | Web End for K Strong Asia |  | WH-015 |  | Translation to be done |  | BKY | 2023-02-05
[5 empty] | Drawing to be approved |  | BKY | 2023-02-03
46 | Saperater |  | PN169 |  | Moulded final sample to be arranged |  | AS | 2023-02-07
Kratos projects
Translation to be done
47 | Horizontal life line |  | PN4000T(100METER) | PNI/R&D/2020-2021/762 | Drawing to be made |  | BKY | 2022-10-11 |  | Not Started | NA | Not Started | Not Started
[5 empty] | TDS & UIM to be made |  | BKY | 2022-08-10
[5 empty] | Translation to be done |  | BKY | 2022-12-10
48 | Guard Rail |  | KGR002(OCT) | PNI/R&D/2021-2022/796 | Assembly to be done |  | BKY | 2022-09-20
[5 empty] | Drawing to be made |  | BKY | 2022-10-08
[5 empty] | Casted Brackets to be ordered for 1000 mtr line |  | BKY | Available
[5 empty] | Straight Base Bracket sample awaited from AB Metal, Quotation awaited |  | AS | 2022-11-30 | final date of samples to be shared
[5 empty] | Angle Base Bracket sample awaited from Mohd Sir |  | AS | 2022-11-30
[5 empty] | Dead Weight Shoe sample moulding to be done |  | BKY | Done
[5 empty] | Communication for Openable variant tesing to be initiated |  | BKY | 15.09.2022
[5 empty] | Openable Sample of Standing Seam variant to be sent for 3rd party testing as well. |  | BKY
[5 empty] | Translation to be done of all variants |  | BKY | 30.09.2022
49 | Permanent Fix Guardrail on concrete |  | KGR002 (OC) | PNI/R&D/2021-2022/797 | Drawing to be made |  | BKY | 2022-10-08
Projects on hold
43 | Door Anchor |  | SA106 | PNI/R&D/2019-2020/672 | Sample to be prepared with Steel ball, Sample to be reviewed |  | APD/BKY | 2021-02-26 |  | Not Started |  | Not Started | Not Started | Hold
45 | Unidirectional Forged Pulley for 6 MM Rope |  | AP30 | PNI/R&D/2020-2021/760 | Drawing to be finalized |  | AS | 2021-02-18 | [5 empty] | Hold
46 | Steel hook |  | PN131N | NA | Assembly done (Discussed with Anant Sir) | KARAM | BKY | 2021-02-23 |  | Not Started |  | Not Started | Not Started | Hold
47 | Descender Block |  | PCGS10AD | PNI/R&D/2017-2018/515 | Casing trials to be done | KARAM | AY | [6 empty] | HOLD
[5 empty] | Testing to be done |  | AS | [6 empty] | HOLD
48 | Descender Block |  | PCGS20AD | PNI/R&D/2014-2015/169 | Casing trials to be done | KARAM | AY | [6 empty] | HOLD
[5 empty] | Testing to be done |  | AS | [6 empty] | HOLD
7 | DBI Sala Uni directional Double Pulley Aluminum |  | SA93S | PNI/R&D/2017-2018/553 | Project sheet to be updated |  | BKY
8 | DI ELECTRIC AUTOMATIC BUCKLE |  | PB029 | PNI/R&D/2017-2018/526 | Hold due to Patent
9 | ROLLER FOR HARNESS |  | PB026 | PNI/R&D/2014-2015/160 | Assembled sample to be review | kratos | BKY
10 | Automatic Decender Cum Rectracteble Block |  | PCGS30AD-R | PNI/R&D/2016-2017/483 | Prototype to be prepared | KARAM | AS
11 | Rope descender |  | PN416 | PNI/R&D/2017-2018/597 | Testing doen with new rope result are not satisfactory | GARY | BKY | [6 empty] | Disscussed with Anant Sir
13 | Guard Rail |  | KGR001 | PNI/R&D/2016-2017/288 | Base plate attcahments new line to be taken | FLS | BKY
14 | Retractable Block |  | PN2002A | PNI/R&D/2016-2017/417 | Final Assembly to be done | KARAM | BKY
15 | Karabiner |  | PN117FBA |  | Testing to be done |  | BKY | [6 empty] | Disscussed with Anant Sir
16 | Karabiner |  | PN118FBA |  | Testing to be done |  | BKY | [6 empty] | Disscussed with Anant Sir
17 | Double Locking Hook |  | PN1010 |  | Drawing to be made |  | AS | Hold
[5 empty] | Gate Investment casting quotation required |  | AS
[5 empty] | Lock in singe part Investment casting quotation required |  | AS
Body Forging tool to be made
Anchorage Eye Forging tool to be made
Body Trimming & Shaving tool to be made
Anchorage Eye Trimming & Shaving tool to be made
Fixtures & Gauges to be made
[5 empty] | Spring, Strip Spring & Double torsion Spring to be sourced |  | BKY
[5 empty] | Rivet to be made |  | BKY
[5 empty] | Product Cost to be prepared |  | PK
[5 empty] | Tool cost to be prepared |  | PK
18 | Double Locking Hook |  | PN1010(OPS) |  | Drawing to be made |  | AS
[5 empty] | Gate Investment casting quotation required |  | AS
[5 empty] | Lock in singe part Investment casting quotation required |  | AS
Body Forging tool to be made
Anchorage Eye Forging tool to be made
Body Trimming & Shaving tool to be made
Anchorage Eye Trimming & Shaving tool to be made
Fixtures & Gauges to be made
[5 empty] | Spring, Strip Spring & Double torsion Spring to be sourced |  | BKY
[5 empty] | Rivet to be made |  | BKY
[5 empty] | Product Cost to be prepared |  | PK
[5 empty] | Tool cost to be prepared |  | PK
19 | Rebar Hook |  | PN1006 | PNI/R&D/2020-2021/715 | 2nd Prototyping to be made |  | BKY | Hold |  | Not Started |  | Not Started | Not Started | Due to Rapid Prototyping machine
14 | BOOM ANCHOR |  | SA117 | PNI/R&D/2020-2021/750 | Drawing to be Approved |  | AS | 2021-03-03 |  | Not Started |  | Not Started | Not Started | Hold
10 | Unidirectional Single Pulley |  | AP020 | PNI/R&D/2016-2017/388 | Drawing to be finalized | KARAM | AS | hold |  | Not Started |  | Not Started | Not Started
31 | Harken Winch |  | PN819 | PNI/R&D/2020-2021/763 | New line to be taken of 20pcs |  | BKY | Hold |  | Not Started |  | Not Started | Not Started
[5 empty] | Drawing to be done |  | AS
43 | Lifeline Crossing |  |  |  | Drawing to be made | Kratos | BKY | Hold |  | Not Started |  | Not Started | Not Started
7 | Openable O Ring |  | OR005 | PNI/R&D/2016-2017/480 | New design to be made |  | AS | Hold |  | Not Started | YES | Not Started | Not Started
34 | New descender (Anthron) |  | RG19 | PNI/R&D/2017-2018/594 | New sample to be prepared | GARY | BKY | 2022-03-09 |  | Not Started | YES | Not Started | Not Started | DISCONTINUED
[5 empty] | Handle forging tool to be made |  | PK | waiting for feedback
| Anchor |  | SA120 |  | Sample to be prepared |  | BKY | HOLD
34 | New descender (Anthron) |  | RG19 | PNI/R&D/2017-2018/594 | New sample to be prepared | GARY | BKY | 2022-03-09 |  | Not Started | YES | Not Started | Not Started | DISCONTINUED
[5 empty] | Handle forging tool to be made |  | PK | waiting for feedback
13 | Spreader Bar |  |  |  | Hold by Indenter |  |  | ??
12 | Rectractable Fall Arrester |  | PN2002N | PNI/R&D/2020-2021/773 | Drawings to be reviewed |  | AS | Hold |  | Not Started | NA | Not Started | Not Started | New Drawing
1 | Ratchet Locking Buckle |  | PB060 | PNI/R&D/2022-2023/830 | Forging tool to be made | KARAM | PK | Hold
[5 empty] | Drawings to be made |  | BKY
6 | Concrete Anchor |  | SA16A(MH) | PNI/R&D/2022-2023/831 | Information shared with Chandresh regarding testing confirmation awaited from Mr. John | K STRONG(USA) | BKY | Hold |  | Not Started | No | Not started | Not Started
[5 empty] | Drawing to be made & Approved |  | BKY
33 | Sky Light Protection |  | WW-01(30) | PNI/R&D/2021-2022/800 | Assembly to be done |  | BKY | Hold |  | NA | NA | Not Started | Not Started
[5 empty] | New design to be made |  | BKY
[5 empty] | Sampe to be arranged from Jacob Sir. |  | BKY

## IMPROVISATION SHEET
Improvisation Status Sheet | [7 empty] | Format No. : QF/RD/26 Rev. No. : 01
Date: 22-06-19
S.No | Product Description | Ref. No. | Status of current actions under plan | Coustomer | Resp | Target Date | Revised Date | Remark
4 |  |  | Cable seal lock to be sourced(quotation awaited) |  | BKY | 2022-10-07
7 |  | SA87 | Testing to be done with kliplock |  | BKY | 2022-11-03
|  |  | Klip Lock Sheet to be installed on fixture |  | BKY | 2022-11-02
15 |  | PB055 | Spring to be sourced wire dia:.45mm & .4 mm |  | BKY
|  | PB011 | Spring to be sourced with 2mm dia reduce |  | BKY | 2023-02-03
18 |  | DA01 | TESTING TO BE DONE WITH Aluminium Square 7075 |  | BKY | 2023-02-06
19 |  | SA116(50) | Drawing to be madewith 50 mm seam clamps & 17mm ID |  | BKY | 2022-11-05
|  | SA07I | Drawing to be made with 50 mm seam clamps & 17 mm id |  | BKY | 2022-11-05
24 |  | DA07 | New design of trolley prototype to be made |  | BKY | 2023-02-20
30 | Dead Wieght Davit | DA07 | Design to be changed with extension |  | BKY | 2023-02-10
25 |  | PN144SS | GATE & Lock new line to be taken (2000 Nos.) |  | BKY
26 |  |  | Ejot testing to be done |  | BKY
27 |  |  | Indus Bracket Drawing to be made |  | BKY
|  |  | Pipe Bending tool to be made |  | PK
28 |  | PN801 | New drawing to be amended with guide pulley |  | BKY
29 |  | PN7000(06) | New design to be shared with Gary |  | BKY | 2022-10-17
32 |  | SA87 | Testing to be done with SA17 Outer Leg Support |  | BKY
|  |  | Sample to be prepared |  | PK
35 |  | PN818 | Body Cover & Base blanking to be done |  | BKY | 2022-12-08
36 | Extension Post for ALU rail | KT-8000(05) | 40 nos. new line to be taken |  | BKY | 2022-12-09
37 | Winch | PN801 | Design to be changed |  | BKY